# Vault AI Systems

# Product Blueprint & Technical Roadmap

Version 3.0

Updated: October 23, 2025

Secure, Fully Plug-and-Play

Enterprise AI Hardware Platform

# Table of Contents

# 1. Executive Summary

Vault AI Systems is developing a secure, air-gapped enterprise AI hardware solution for organizations requiring on-premises AI capabilities without internet connectivity. Our target customers include universities, law firms, healthcare organizations, and enterprises with strict data sovereignty requirements.

The product is a fully integrated hardware unit (workstation/server) pre-configured with enterprise-grade AI infrastructure, including GPU hardware, optimized OS, containerized AI frameworks, and a locally-hosted large language model. Target price point: $40,000-$60,000 per unit.

Key differentiator: Lambda Labs recently exited the enterprise AI workstation space, creating a market opportunity for a secure, air-gapped solution with superior customer support and enterprise features.

# 2. Product Vision & Positioning

## 2.1 Core Value Proposition

- Secure & Air-Gapped: Complete AI infrastructure that operates without internet connectivity

- Plug-and-Play: Pre-configured hardware and software ready for immediate use

- Enterprise-Grade: Hardened OS, professional management tools, and comprehensive monitoring

- Starting Ground: Foundation for internal AI initiatives without vendor lock-in

## 2.2 Target Markets

- Universities & Research Institutions: AI research labs, computer science departments

- Legal & Professional Services: Law firms requiring confidential document analysis

- Healthcare: HIPAA-compliant AI for medical records and diagnostics

- Government & Defense: Secure AI for classified or sensitive operations

- Financial Services: Regulated industries requiring on-premises AI

# 3. Technical Architecture

## 3.1 Hardware Specifications (Target)

- GPU: 2x NVIDIA RTX 4090 (48GB total VRAM) or similar enterprise GPU

- CPU: AMD Ryzen Threadripper or Intel Xeon (32+ cores)

- RAM: 128GB+ DDR5

- Storage: 2TB+ NVMe SSD (OS & models) + 4TB+ data drives

- Form Factor: Tower workstation or 4U rackmount server

Note: Hardware specifications to be finalized by November 2025

## 3.2 Software Stack

- Operating System: Ubuntu 22.04 LTS (with future upgrade path to Ubuntu Pro)

- Security Hardening: CIS Level 1 benchmarks, DISA STIG compliance preparation

- AI Frameworks: PyTorch, vLLM, CUDA toolkit, Hugging Face Transformers

- Inference Engines: vLLM, ONNX Runtime, TensorRT

- Management Tools: Cockpit (web UI), Prometheus + Grafana (monitoring)

- Containerization: Docker + NVIDIA Container Toolkit

- Pre-loaded LLM: Options include Qwen 3 32B, DeepSeek R1, GLM 4.5 Air (2B model for MVP development)

# 4. Development Timeline & Milestones

## 4.1 Critical Timeline

- Hardware Finalization: November 2025

- First Assembled Unit: Late January 2026

- MVP Scope: Solid foundation, some corners cut for speed, but production-ready

Note: Software development proceeds in parallel with hardware procurement

## 4.2 Week 1 Immediate Tasks

- Order hardware (GPU procurement critical due to lead times)

- Set up apt-mirror server for offline package repository

- Install Packer + Ansible on development workstation

- Test Cockpit for system management UI

- Begin MacBook-friendly tasks from Epic 1 (see Section 6.1)

# 5. Product Epics Overview

The product roadmap is organized into five major epics, with Epics 1 and 2 containing detailed technical tasks outlined in Section 6.

| Epic | Goal | Status |
| --- | --- | --- |
| Epic 1 | Golden Image Automation - Create repeatable, automated OS image with security hardening | Detailed Tasks in Section 6.1 |
| Epic 2 | Pre-Installed AI Stack - Install and configure all AI frameworks and tools | Detailed Tasks in Section 6.2 |
| Epic 3 | Demo & Management Interface - Build user-facing dashboards, chat UI, and monitoring | Tasks in Development |
| Epic 4 | Air-Gapped Update Delivery - Create offline update mechanism using APT mirror and USB transfer | Tasks in Development |
| Epic 5 | Customer Enablement - Create documentation, first-boot guide, and support materials | Tasks in Development |

# 6. Detailed Epic Tasks

## 6.1 Epic 1: Golden Image Automation

Goal: Create a repeatable, automated pipeline for building the base operating system image with security hardening, drivers, and core infrastructure.

Key Technologies: Packer (image building), Ansible (configuration management), Ubuntu 22.04 LTS

Critical Note: Approximately 70% of Epic 1 tasks can be completed on MacBook Pro before GPU hardware arrives. Tasks marked with ✅ are MacBook-friendly; tasks marked with ❌ require GPU hardware.

| Task | Description | Effort | MacBook Friendly |
| --- | --- | --- | --- |
| Task 1.1 | Development Environment Setup: Install VirtualBox/UTM, download Ubuntu ISO, create test VM | 2 hours | ✅ Yes |
| Task 1.2 | Git Repository Setup: Create project structure with folders for Packer, Ansible, scripts, docs | 1 hour | ✅ Yes |
| Task 1.3 | Packer Template: Create base Ubuntu 22.04 template with automated installation (preseed/cloud-init) | 4-6 hours | ✅ Yes |
| Task 1.4 | Ansible Playbooks - Base System: Create playbooks for system updates, package installation, user setup | 4 hours | ✅ Yes |
| Task 1.5 | CIS Hardening: Write Ansible playbook implementing CIS Level 1 benchmarks for Ubuntu | 6 hours | ✅ Yes |
| Task 1.6 | Docker Installation: Ansible playbook for Docker Engine, containerd, docker-compose | 3 hours | ✅ Yes |
| Task 1.7 | Python & ML Tools: Install Python 3.10+, pip, virtualenv, common ML libraries | 3 hours | ✅ Yes |
| Task 1.8 | NVIDIA Driver Installation: Install and configure NVIDIA GPU drivers, CUDA toolkit | 4 hours | ❌ GPU Required |
| Task 1.9 | NVIDIA Container Toolkit: Enable Docker GPU access via NVIDIA Container Toolkit | 2 hours | ❌ GPU Required |
| Task 1.10 | Integration Testing: Build complete golden image on real hardware, verify all components | 4-6 hours | ❌ GPU Required |

Total Estimated Effort: 30-40 hours (70% can start immediately on MacBook)

## 6.2 Epic 2: Pre-Installed AI Stack

Goal: Install and configure all AI frameworks, tools, and dependencies required for running LLMs and ML workloads.

Key Technologies: PyTorch, vLLM, CUDA, Hugging Face, ONNX Runtime, TensorRT, DeepSpeed

Critical Note: All Epic 2 tasks require GPU hardware and depend on completion of Epic 1 Task 1.8 (NVIDIA drivers).

| Task | Description | Effort | Dependencies |
| --- | --- | --- | --- |
| Task 2.1 | PyTorch Installation: Install PyTorch 2.x with CUDA 12.1+ support, verify GPU access | 3 hours | Epic 1 Task 1.8 |
| Task 2.2 | CUDA Toolkit & cuDNN: Install NVIDIA CUDA toolkit, cuDNN libraries, verify compatibility | 4 hours | Epic 1 Task 1.8 |
| Task 2.3 | vLLM Container Setup: Build Docker container with vLLM, configure for optimal GPU utilization | 6 hours | Tasks 2.1, 2.2 |
| Task 2.4 | Hugging Face Transformers: Install Transformers library, Tokenizers, Datasets, configure model cache | 2 hours | Task 2.1 |
| Task 2.5 | ONNX Runtime: Install ONNX Runtime with GPU support for cross-framework model deployment | 2 hours | Task 2.2 |
| Task 2.6 | TensorRT: Install TensorRT for optimized NVIDIA GPU inference (up to 6x faster) | 3 hours | Task 2.2 |
| Task 2.7 | DeepSpeed: Install DeepSpeed for LLM fine-tuning and distributed training capabilities | 2 hours | Task 2.1 |
| Task 2.8 | Pre-load 2B Model: Download and pre-load small 2B parameter model (e.g., Qwen 2B) for MVP testing | 4 hours | Tasks 2.3, 2.4 |
| Task 2.9 | Testing & Validation: Run inference tests, verify GPU utilization, benchmark performance | 4 hours | All previous tasks |

Total Estimated Effort: 30-35 hours (requires GPU hardware)

# 7. Immediate Next Steps & Action Items

## 7.1 This Week (October 23-30, 2025)

### Hardware Team

- Finalize GPU selection and place orders (CRITICAL: 2-4 week lead time)

- Order USB drives (256GB+) for repository transfers

- Procure storage for apt-mirror server (100GB+ minimum)

### Software Team

- Set up Ubuntu 22.04 LTS server for apt-mirror

- Configure /etc/apt/mirror.list and start first sync

- Install Packer + Ansible on dev workstation

- Install and test Cockpit for system management

- Begin Epic 1 MacBook-friendly tasks (Tasks 1.1-1.7)

### Leadership (CTO)

- Review and approve this Product Blueprint

- Assign team members to Hardware/Software tracks

- Create shared Git repository for infrastructure-as-code

- Schedule weekly progress reviews

## 7.2 Critical Decisions Needed by November 15

- LLM Model Selection: Qwen 3 32B vs DeepSeek R1 vs others for production deployment

- Repository Scope: 70-100GB selective mirror vs 450GB full mirror

- Demo UI Framework: Gradio vs Streamlit for chat interface

- Dashboard Strategy: Grafana-based unified dashboard vs separate tools

## 7.3 MVP Success Metrics (by November 15, 2025)

- ✅ Hardware ordered with confirmed delivery dates

- ✅ Working apt-mirror with verified Ubuntu packages

- ✅ Packer + Ansible pipeline producing bootable images

- ✅ PyTorch and core AI frameworks installed

- ✅ vLLM container running with 2B model

- ✅ Cockpit configured for system management

# 8. Risk Register & Mitigation Strategies

| Risk | Impact | Mitigation |
| --- | --- | --- |
| GPU supply shortage / long lead times | Delays entire hardware timeline, pushes January delivery | Order immediately, identify alternative GPU options, pre-order backup units |
| Offline update mechanism complexity | Technical challenges in APT mirroring, USB transfer workflow | Use proven apt-mirror approach, detailed documentation, thorough testing |
| LLM model size vs hardware constraints | 32B+ models may not fit in 48GB VRAM with overhead | Test with 2B model first, use quantization, offer multiple model size options |
| Integration complexity across tools | Cockpit, Grafana, vLLM, chat UI may not integrate smoothly | Test integrations early, create unified Grafana landing page |
| Lack of customer feedback before launch | Building product without validating assumptions with target customers | Identify 2-3 pilot customers, conduct user testing of MVP in December |

# 9. Document Control & Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | Oct 20, 2025 | CTO / AI Assistant | Initial blueprint with 5 epics and technical architecture |
| 2.0 | Oct 21, 2025 | CTO / AI Assistant | Added research findings, revised epics, removed MAAS/Harbor, updated offline update mechanism |
| 3.0 | Oct 23, 2025 | CTO / AI Assistant | Added detailed task breakdowns for Epic 1 and Epic 2 with effort estimates and dependencies |

End of Document

For questions or updates, contact the CTO